## Read Me & Charter
Halo Collar ML — Engagement Operating System
Halo × Edge Impulse × Softeq ¦ Source of truth for plan, ownership, risks & decisions ¦ Snapshot: 23 Jun 2026
Purpose
Two on-device ML deliverables for the HALO 5 collar: (1) a GPS indoor/outdoor place-recognition model and (2) an Activity active/idle model. Lab accuracy is solved on both; the open work is field validation, two-model on-device integration, data coverage, and agreeing v1 goals. This workbook is the shared PM layer on top of the existing status tracker — use it to drive ownership and unblock progress.
Parties & team roster
⚠ Confirm org mapping — inferred from the tracker; correct any cell highlighted yellow.
| Party | Role in engagement | Named team
| Halo | Product owner / device & firmware / decision authority | Vitaly (lead/decisions), Chris (product/use-cases), Timour (technical), Eigor (firmware)
| Edge Impulse | Platform + on-device enablement, SDK integration, validation methodology | Patrick, Ashvin
| Softeq | 3rd-party ML consultancy — model development, features, data cleaning & labeling | Dinko (ML lead), Adrian (data/labeling)
Targets (to validate, not contractual)
| Metric | Current | v1 / Phase 1 target | Phase 2 target
| GPS — lab accuracy | ~94–95% (Done) | Hold | Hold
| GPS — on-device accuracy | ~90% (manual) | ~95% objective | Maintain in field
| Activity — lab accuracy | ~97.6% 8-class (Done) | 2-class deployed | —
| Activity — on-device accuracy | Not yet measured | Objective baseline | Improve iteratively
| Real-world (both) | Below lab, unmeasured | 80–85% | 90%+
| Model footprint | GPS ~20KB | Within budget | Within budget
How to use this workbook
| Tab | What it's for
| Project Plan | The work breakdown: every open action with owner, dependency, priority and a target date driven by the Plan date cell below.
| RACI | Who is Responsible / Accountable / Consulted / Informed across the three parties for each activity. Fixes the ownership ambiguity.
| Risks & Blockers | Live register of what's stopping progress, with severity, owner and mitigation.
| Decisions Needed | Open questions that block work — mostly Halo business decisions. Resolve these to unstick the program.
| Status Dashboard | Auto-rollup of plan status, risk severity and open decisions. Read this first in reviews.
| Plan date (drives target dates): |  | 2026-06-23

## Project Plan
Project Plan — Work Breakdown
Open actions across both models + cross-cutting workstreams. Target date = Plan date + offset (days). Update Status as work moves.
ID | Workstream | Phase | Next action | Status | Accountable | Lead | Depends on | Priority | Offset(d) | Target date | Key risk / note
C1 | Cross-cutting | Goal & criteria | Confirm v1 goal, per-class business value & success criteria with Halo | Needs definition | Halo | Vitaly | — | NOW | 11 | 2026-07-04 | Scope & success undefined until set
C2 | Cross-cutting | Validation & DoD | Agree definition of 'done' + objective validation method (pilot video ground-truth) | Needs definition | Edge Impulse | Patrick | C1 | NOW | 4 | 2026-06-27 | Progress can't be proven without it
C3 | Cross-cutting | Two-model on device | Merge branches; enable GPS + activity to run together on collar (resolve SDK limit) | In progress | Edge Impulse | Ashvin | — | NOW | 11 | 2026-07-04 | Firmware/SDK limit; Eigor needed
C4 | Cross-cutting | Test harness | Build repeatable on-device test method (same routes/time; labelled batches) | Needs definition | Edge Impulse | Patrick | C2 | NEXT | 18 | 2026-07-11 | No repeatable re-test today
G1 | GPS model | 1 Data | Collect representative US dataset (homes/window types); agree borderline labelling | In progress | Softeq | Adrian | — | NEXT | 30 | 2026-07-23 | Thin varied-environment coverage
G2 | GPS model | 2 Features | Maintain ~50-feature set; retrain as new data arrives | Done | Softeq | Dinko | G1 | LATER | 60 | 2026-08-22 | —
G3 | GPS model | 3 Lab accuracy | Hold ~94–95% lab; keep reporting in status | Done | Softeq | Dinko | — | — | 0 | done | —
G4 | GPS model | 4 Install (GPS) | Handed to Edge Impulse for combined two-model build | Done | Softeq→EI | Dinko | — | — | 0 | done | —
G5 | GPS model | 6 On-device acc. | Run labelled batches on collar for objective figure (~95% target) | In progress | Edge Impulse | Ashvin | C3, C4 | NEXT | 14 | 2026-07-07 | Move from manual walk tests to batch
G6 | GPS model | 7 Real-world | Roll single GPS model to small group; measure w/ agreed method; add house-geofence backup | Blocked | Halo | Chris | C2, G1 | NEXT | 21 | 2026-07-14 | Lab-to-field drop unmeasured
A1 | Activity model | 1 Data | Label toward ~20–40h (more dogs/orientations); finalise posture-vs-behavior taxonomy | In progress | Softeq | Adrian | C1 | NEXT | 30 | 2026-07-23 | ~7–10h of ~20–40h; narrow data
A2 | Activity model | 2 Features | Use orientation-robust features for v1; plan orientation normalisation | Done | Softeq | Dinko | — | LATER | 60 | 2026-08-22 | Orientation-sensitive features deferred
A3 | Activity model | 3 Lab accuracy | Present lab (~97.6% 8-class) vs field side-by-side to set expectations | Done | Softeq | Dinko | — | — | 0 | done | Lab figure overstates field
A4 | Activity model | 4 Install (2-class) | Edge Impulse enables 2-class active/idle model on collar for client trial | Ready to deploy | Edge Impulse | Ashvin | — | NOW | 11 | 2026-07-04 | Awaiting on-device enable
A5 | Activity model | 6 On-device acc. | Replay labelled batches on collar for objective number (same method as GPS) | Not started | Edge Impulse | Ashvin | A4, C3, C4 | NEXT | 21 | 2026-07-14 | Not yet tested on device
A6 | Activity model | 7 Real-world | Deploy 2-class to user group; measure; compare rule-based vs model for v1 | Blocked | Halo | Chris | C2, A1, A4 | NEXT | 28 | 2026-07-21 | Field below lab
Formulas:
Target date = IF([Offset(d)]>0,'Read Me & Charter'!$D31+[Offset(d)],"done")

## RACI
RACI — Roles & Accountability
R=Responsible (does the work) · A=Accountable (one owner, sign-off) · C=Consulted · I=Informed. ⚠ Proposed — confirm with the three parties.
ID | Activity | Halo | Edge Impulse | Softeq | Accountable lead | Notes
R1 | Define v1 goal & success criteria | A/R | C | C | Vitaly (Halo) | Blocks everything downstream
R2 | Define per-class business value / desired outcomes | A | C | C | Halo | Raised by Edge Impulse
R3 | Data collection & labeling campaigns | A | I | R | Halo + Adrian (Softeq) | Halo supplies users/devices; Softeq labels/cleans
R4 | Feature engineering & model development | I | C | A/R | Dinko (Softeq) | —
R5 | Lab accuracy validation | I | C | A/R | Dinko (Softeq) | Done on both models
R6 | On-device model enablement (single model) | C | A/R | C | Ashvin (Edge Impulse) | Halo firmware (Eigor) consulted
R7 | Two-model SDK integration | C | A/R | C | Ashvin (Edge Impulse) | Eigor to join Monday session
R8 | On-device objective accuracy testing | I | A | R | Edge Impulse + Dinko | Batch-replay method
R9 | Define validation method & 'definition of done' | C | A/R | C | Patrick (Edge Impulse) | EI engaged for methodology; Halo approves DoD
R10 | Field / real-world testing & rollout | A/R | C | C | Chris (Halo) | Small user group first
R11 | Repeatable test harness / procedure | C | A/R | R | Edge Impulse | Fixed routes/time; productionise later
R12 | Firmware changes on collar | A/R | C | I | Eigor (Halo) | Dependency for two-model build
R13 | Program status reporting & cadence | C | A/R | C | Patrick (Edge Impulse) | Weekly sync + bi-weekly leadership
Legend: A/R = Accountable & Responsible · A = Accountable (sign-off) · R = Responsible (does work) · C = Consulted · I = Informed

## Risks & Blockers
Risk & Blocker Register
Impact & Likelihood scored 1–3. Score = Impact × Likelihood. Rating auto-derives. Work the Critical/High open items first.
ID | Type | Title | Description | Workstream | Owner | Impact | Likelihood | Score | Rating | Status | Mitigation / next step
K1 | Blocker | Two models can't run on device together | Firmware/SDK can't run GPS + activity simultaneously — blocks a combined v1 | Two-model | Ashvin (EI) | 3 | 3 | 9 | Critical | Open | Merge branches; Monday SDK session w/ Eigor; evaluate parallel vs merged
K2 | Blocker | No validation method / definition of done | Performance judged by reviewer impression; progress can't be measured | Validation | Patrick (EI) + Halo | 3 | 3 | 9 | Critical | Open | Agree DoD + objective method; pilot video ground-truth on small set
K3 | Decision | v1 goal & per-class value unconfirmed | Without desired outcomes per class, scope & success are undefined | Goal | Vitaly (Halo) | 3 | 3 | 9 | Critical | Open | Halo confirms use cases, real-time vs accumulated, value per class
K4 | Risk | Activity data thin & narrow | ~7–10h of ~20–40h target; few dogs/orientations; edge cases under-represented | Activity data | Adrian (Softeq) + Halo | 3 | 3 | 9 | Critical | Open | Label to target; more dogs/orientations; improve in-app labeling; small video calibration set
K5 | Risk | GPS environment coverage thin | US homes/window types/covered-outdoor under-represented; per-home variation | GPS data | Adrian (Softeq) + Halo | 3 | 2 | 6 | Critical | Open | Representative US collection; agree borderline labelling; house-geofence backup
K6 | Risk | Lab-to-field accuracy drop unmeasured | Field lower than lab but not objectively measured on either model | Both | Halo + Group | 3 | 3 | 9 | Critical | Open | Objective on-device + field measurement once method agreed
K7 | Risk | No repeatable test environment | Cannot re-test same locations/time to compare runs | Test harness | Patrick (EI) | 2 | 3 | 6 | Critical | Open | Build repeatable batch-replay harness; fixed routes
K8 | Risk | Firmware dependency on Halo (Eigor) | Two-model build & firmware tweaks depend on Halo firmware availability | Firmware | Eigor (Halo) | 2 | 2 | 4 | High | Open | Eigor joins Monday session; schedule firmware support windows
K9 | Risk | Orientation-sensitive features | Strong features depend on collar orientation — main lab-vs-field cause | Activity model | Dinko (Softeq) | 2 | 2 | 4 | High | Mitigated (v1) | v1 uses orientation-robust features; add orientation normalisation before multiclass

## Decisions Needed
Decisions Needed — Open Questions
Mostly Halo business decisions that block the team. Resolving these is the fastest way to unstick the program.
ID | Decision / open question | Why it matters (what it blocks) | Decider | Priority | Status | Notes / options
D1 | What is the v1 goal & desired outcome for each class? | Defines scope & success; blocks validation and data targets | Halo (Vitaly) | NOW | Open | Edge Impulse question: business value of each class
D2 | Real-time status vs accumulated data per hour? | Changes how the model is used and validated | Halo | NOW | Open | Raised by Dinko (both models)
D3 | Formal definition of 'active' (activity model) | No threshold or DoD possible without it | Halo + Group | NOW | Open | Consider one tunable active/idle threshold
D4 | Definition of 'done' + validation method | Can't prove accuracy or progress objectively | Edge Impulse + Halo | NOW | Open | Video ground-truth pilot; objective batch replay
D5 | Two models: run in parallel vs merged single model? | Determines the SDK integration approach | EI + Halo firmware | NOW | Open | Timour: run in parallel, not merged
D6 | Rule-based vs model approach for activity v1? | A simpler v1 may meet the near-term need | Group | NEXT | Open | Chris: 8-class is more than current need
D7 | Add GPS house-geofence / map backup in v1? | High value — most use is 'in my own house' | Halo | NEXT | Open | Backup check for near-window cases
D8 | Scope of video ground-truth? | Broad video capture is a heavy lift | Group | NEXT | Open | Scope to a small calibration set

## Status Dashboard
Status Dashboard
Auto-rollup from the other tabs. Read this first in reviews. Snapshot driven by Plan date on the Charter tab.
Action status (Project Plan)
| Status | Count
| Not started | 1
| Needs definition | 3
| In progress | 4
| Ready to deploy | 1
| Blocked | 2
| Done | 5
| Total open (not Done) | 11
Risks & blockers by rating
| Rating | Count
| Critical | 7
| High | 2
| Medium | 0
| Low | 0
| Open blockers | 2
Decisions needed
| Open decisions | 8
| …of which NOW priority | 5
This week — NOW priorities
1. Halo confirms v1 goal, per-class business value & success criteria (D1, C1)
2. Agree definition of 'done' + validation method (D4, C2)
3. Edge Impulse enables 2-class activity model + merges two-model build (A4, C3)
4. Decide parallel vs merged two-model approach — Eigor in Monday session (D5)